## Test Cases
TC ID | ADO Work Item | Module / Screen | Test Case Title | Test Objective | Preconditions | Test Steps | Test Data | Expected Result | Test Type | Priority | Status | Actual Result | Defect ID | Comments
TC-DJ-001 | 44664 | Add Job Modal - Draft Job | Verify 'Assign temporary job number' checkbox is available in Add Job modal | Ensure the draft-job option is exposed on the existing Add Job modal | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open the Open Jobs dashboard 2. Click the Add Job button 3. Observe the Add Existing Job modal, below the Job Number dropdown | N/A | A checkbox labeled 'Assign temporary job number' is displayed under the Job Number dropdown; layout/styling matches the Figma wireframes | UI / Functional | High | Pass | 'Assign temporary job number' checkbox displays under the Job Number field in the Add existing job modal.
TC-DJ-002 | 44664 | Add Job Modal - Draft Job | Verify Job Number dropdown is disabled when draft checkbox is checked | Confirm draft intent disables manual job selection | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select ONE service offering and click Apply 3. Check 'Assign temporary job number' 4. Observe the Job Number dropdown | 1 service offering | Job Number dropdown is disabled while the draft checkbox is checked | Functional | High | Pass | With one offering (Commercial Scaffolding) applied, checking the checkbox disabled the Job Number field (input disabled=true).
TC-DJ-003 | 44664 | Add Job Modal - Draft Job | Verify error when multiple service offerings are selected for a draft job | Enforce the single-service-offering rule for drafts | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select TWO or more service offerings and click Apply 3. Check 'Assign temporary job number' | 2+ service offerings | An error message is displayed on the modal stating that only one service offering can be selected when creating a draft job; draft creation is prevented | Negative | High | Pass | Red error shown: 'Only one service offering type can be selected when creating a draft job.' Draft creation prevented.
TC-DJ-004 | 44664 | Add Job Modal - Draft Job | Verify selected job number is cleared when draft checkbox is checked | Confirm mutually exclusive job selection vs draft creation | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select one service offering and click Apply 3. Select a job number from the Job Number dropdown 4. Check 'Assign temporary job number' | 1 offering + any unpublished job | The previously selected job number is cleared and the Job Number dropdown becomes disabled | Functional | Medium | Pass | Selected job 00102 was cleared and the Job Number field disabled when the draft checkbox was checked.
TC-DJ-005 | 44664 | Add Job Modal - Draft Job | Verify draft job is created and user lands on Step 1 | Validate the draft job happy path | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select one service offering and click Apply 3. Check 'Assign temporary job number' 4. Click Add | 1 service offering | User is taken to Job Workbench Step 1; a draft job is created with a system-generated temporary job number tied to the selected service offering | Functional | High | Pass | Draft created with temp number DRAFT-11 (later DRAFT-12); user taken to Job Workbench Step 1 - General details.
TC-DJ-006 | 44664 | Add Job Modal - Draft Job | Verify Cancel does not create a draft job | Confirm cancel path leaves no orphan draft | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select one service offering and click Apply 3. Check 'Assign temporary job number' 4. Click Cancel 5. Search the Open Jobs dashboard for a new temp job | 1 service offering | Modal closes; user remains on the Open Jobs dashboard; no draft job is created | Functional | Medium | Pass | Cancel closed the modal; user remained on /jobs/open; no new draft appeared (only DRAFT-06/08/10 present).
TC-DJ-007 | 44664 | Add Job Modal - Draft Job | Regression - Job Number dropdown filtered by service offering and unpublished status | Confirm existing Add Job behavior is unchanged | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select one service offering, click Apply, review Job Number dropdown 3. Repeat with multiple service offerings | Offerings with known unpublished jobs | Dropdown lists only jobs that are not previously published and belong to the selected service offering(s) | Regression | Medium | Pass | Job list filtered by offering (e.g. 306 Insulation jobs vs 2,452 for All); only unpublished jobs listed. |  | Numbered draft jobs are not listed, but see BUG-02 for 'null -' entries.
TC-DJ-008 | 44664 | Add Job Modal - Draft Job | Regression - Add existing (non-draft) job navigates to Step 1 read-only; Cancel closes modal | Confirm the existing add-job flow still works | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select offering(s), click Apply 3. Select a job number and click Add; verify landing page 4. Re-open modal, select a job, click Cancel | Any unpublished job | Add: user is taken to Step 1 and the Details section is read-only. Cancel: modal closes and user remains on the Open Jobs dashboard | Regression | Medium | Pass | Add of existing job 00102 landed on Step 1 with Details fields read-only (job no, description, customer, phone, offering, billing type greyed). Cancel closes modal leaving user on dashboard.
TC-DJ-009 | 44664 | Add Job Modal - Draft Job | Regression - 'All' service offering shows all unpublished jobs | Confirm the All option is unaffected | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select the 'All' service offering option and click Apply 3. Review the Job Number dropdown | N/A | All unpublished jobs are listed regardless of service offering | Regression | Low | Pass | 'All' returned 2,452 jobs across all service offerings. | BUG-02 | 5 options render as 'null -' at the top of the list - defect BUG-02.
TC-DJ-010 | 44664 | Add Job Modal - Draft Job | Regression - validation error when Add is clicked without a job number | Confirm required-field validation still fires | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open Add Job modal 2. Select a service offering and click Apply 3. Without selecting a job number (and without checking the draft checkbox), click Add | N/A | An error is shown telling the coordinator to select a job number; no navigation occurs | Regression / Negative | Medium | Fail | Clicking Add without a job number shows generic message 'Missing or invalid information provided.' with the Job number field highlighted red; it does not tell the coordinator to select a job number. | BUG-01 | Low severity - validation fires and blocks, but message wording does not match AC.
TC-DJ-011 | 44665 | Job Workbench - Step 1 Draft Details | Verify draft warning message on Step 1 General Details | Ensure coordinators are warned about the draft state | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the draft job 2. Go to Step 1 - General Details 3. Observe the Details section | Draft job with temp number | Warning is displayed: 'This job currently has a temporary job number assigned and is in draft state. Timesheets cannot be approved until the job number is updated.' | Functional | High | Pass | Warning displayed verbatim: 'This job currently has a temporary job number assigned and is in draft state. Timesheets cannot be approved until the job number is updated.'
TC-DJ-012 | 44665 | Job Workbench - Step 1 Draft Details | Verify Details section fields are disabled for a draft job | Confirm draft-aware Details card behavior | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the draft job at Step 1 2. Attempt to interact with each field in the Details section | Draft job | Fields in the Details section are disabled per the acceptance criteria; customer name, customer phone and billing type are blank/disabled; service offering is pre-filled and read-only; styling matches Figma | Functional / UI | High | Pass | All Details fields disabled for the draft (job number, description, customer name/phone blank+disabled, offering pre-filled read-only, billing type blank). |  | Observation for BA: story narrative says coordinator should be able to fill the job description, but the field is disabled (AC says all disabled - AC honoured).
TC-DJ-013 | 44665 | Job Workbench - Step 1 Draft Details | Verify temporary job number is shown as a read-only draft label | Confirm the temp number presentation on Step 1 | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the draft job at Step 1 2. Observe the Job Number field/label | Draft job | The system-generated temporary job number is displayed as a read-only draft label (it cannot be edited) | UI | Medium | Pass | Temp number (DRAFT-11 / DRAFT-12) shown as a read-only value in the Job number field.
TC-DJ-014 | 44665 | Job Workbench - Step 1 Draft Details | Verify 'Link to a J&E job number' button renders only while the job is a draft | Confirm the link entry point visibility rules | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the draft job at Step 1 and observe the Details section 2. Link the job to a J&E number (see link flow) 3. Re-open Step 1 and observe again | Draft job; valid J&E job number | Before linking, the 'Link to a J&E job number' button is visible in the Details section; after the job is linked (IsDraft = false), the button is no longer shown | Functional | High | Pass | Link entry point rendered in Details while draft; after linking to 00106 the button disappeared. |  | Button is labelled 'Update' (per story 44666 AC), not 'Link to a J&E job number' as 44665 tech note suggests.
TC-DJ-015 | 44666 | Job Workbench - Link to J&E Number | Verify link modal opens pre-populated with locked service offering | Validate the link-mode variant of the Add Existing Job modal | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the draft job at Step 1 2. Click the Update / 'Link to a J&E job number' button 3. Observe the Add Existing Job modal | Draft job | Modal is presented with the draft's service offering pre-populated and not changeable; red message shown: 'Important - All associated Tasks, Activities, Dispatches, and Timesheets will be transferred from this temporary job number and updated to the job number'; checkbox 'I acknowledge and approve this update.' is present; styling matches Figma | Functional / UI | High | Pass | 'Select an existing job' modal opened with the draft's offering pre-populated and read-only (Mui-readOnly, dropdown will not open); red Important message and 'I acknowledge and approve this update.' checkbox present. |  | Message copy differs slightly from AC and adds 'This action is permanent and cannot be reversed.' - improvement, not a defect.
TC-DJ-016 | 44666 | Job Workbench - Link to J&E Number | Verify Update stays disabled until acknowledgement is checked | Enforce explicit acknowledgement before linking | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the link modal from Step 1 2. Select a J&E job number 3. Leave the acknowledge checkbox unchecked and observe the Update button 4. Check the acknowledge checkbox and observe again | Valid J&E job number | With the checkbox unchecked the Update button is disabled; after checking 'I acknowledge and approve this update.' the Update button becomes enabled | Functional | High | Pass | With job 00106 selected and checkbox unchecked, Update disabled; after checking acknowledgement, Update enabled.
TC-DJ-017 | 44666 | Job Workbench - Link to J&E Number | Verify Cancel from link modal keeps the job in draft | Confirm no accidental linking on cancel | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the link modal 2. Select a J&E job number 3. Click Cancel | Valid J&E job number | The job is not linked and remains in draft mode with its temporary job number | Functional | Medium | Pass | Cancel closed the modal; job remained DRAFT-11 in draft state.
TC-DJ-018 | 44666 | Job Workbench - Link to J&E Number | Verify Cancel from the link confirmation modal | Confirm the confirmation step can be aborted | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the link modal, select a job, check acknowledge, click Update 2. On the link confirmation modal, click Cancel | Valid J&E job number | The job is not linked; the user is returned to Step 1 with the job still in draft state | Functional | Medium | Fail | No link confirmation modal exists. Clicking Update executes the link immediately - there is no second Cancel/Link step as required by the AC. | BUG-02 | Medium - the irreversible transfer happens with no final confirmation beyond the acknowledge checkbox.
TC-DJ-019 | 44666 | Job Workbench - Link to J&E Number | Verify successful link to J&E job number | Validate the link happy path | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the link modal, select a J&E job number, check acknowledge, click Update 2. On the confirmation modal, click Link 3. Observe Step 1 Details | Valid J&E job number with no existing FieldTrax work | Modal closes; Details section updates to read-only with the J&E job info displayed; green success toast 'Job number assigned successfully' appears; the temporary number is replaced by the official job number | Functional | High | Pass | Link executed: Details became read-only with 00106 / ETPC TP STAIR CASE SCAFFOLD / ETPC COMPANY LLC / Lump Sum; green toast 'Job number assigned successfully' observed (on DRAFT-06 -> 00136 run); temp number replaced. |  | Confirmation-modal step skipped because of BUG-05.
TC-DJ-020 | 44666 | Job Workbench - Link to J&E Number | Verify error when linking to a J&E job that already has work in FieldTrax | Validate the conflict (409) handling in the UI | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the link modal 2. Select a J&E job that already has its own tasks/documents in FieldTrax 3. Check acknowledge, click Update and confirm Link | J&E job with existing tasks/documents | Link is rejected and the error is shown: 'This J&E job already has work in FieldTrax and can't be linked to a draft. Open it directly instead.' The draft job is unchanged | Negative | High | Pass | Linking DRAFT-10 to 00153 (job with existing FieldTrax work) was rejected with the exact message: 'This J&E job already has work in FieldTrax and can't be linked to a draft. Open it directly instead.' Draft unchanged.
TC-DJ-021 | 44666 | Job Workbench - Link to J&E Number | Verify all related records are retained after linking | Confirm GUID-retention: documents, craft mappings, tasks, dispatches and timesheets survive the link | Draft job exists with attached documents, craft codes, tasks, at least one dispatch and logged time | 1. Note the documents, craft codes, tasks, dispatches and timesheet hours on the draft job 2. Link the draft to a J&E job number 3. Re-open the job and each related area | Draft job with attached work items | Every related record previously attached to the draft is present under the official job number; no data is lost and no duplicate/second job row is created | End-to-End | High | Pass | DRAFT-06 -> 00136: attached document (Screenshot ...png), task grouping 'Setting up testing groups', task 'New task 1', activity and $20.00 craft mix all retained under 00136; same job GUID, no duplicate row.
TC-DJ-022 | 44676 | Timesheet Approval - Draft Guard | Verify approval is blocked for a timesheet containing draft-job hours | Ensure the approver cannot approve time on a draft job | User is logged into FieldTrax web as an Approver; a pending timesheet exists that includes hours logged against a draft (temporary) job | 1. Open Pending Timesheets 2. Select a pending timesheet that includes hours against a draft job 3. Click Approve | Timesheet with draft-job hours | A modal is displayed: 'The timesheet includes hours on a draft job and can't be approved until the job is linked to a J&E job'; the timesheet is NOT approved | Functional / Negative | High | Pass | 'Draft job hours' modal displayed: 'The timesheet includes hours on a draft job and can't be approved until the job is linked to a J&E job' with per-employee detail (Arjun Porwal - 5.38 hours). Timesheet NOT approved.
TC-DJ-023 | 44676 | Timesheet Approval - Draft Guard | Verify temp-job warning banner at the top of the timesheet | Ensure the approver is warned before attempting approval | User is logged into FieldTrax web as an Approver; a pending timesheet exists that includes hours logged against a draft (temporary) job | 1. Open a timesheet that has hours logged against a temporary job 2. Observe the top of the timesheet | Timesheet with X hours on a temp job | Warning is displayed: 'There are X hours assigned to temporary job number. Coordinator must assign these activities to a job number before approving.' with the correct hours value; styling matches Figma | Functional / UI | High | Pass | Banner at top of timesheet: 'There are 05:23 hours assigned to temporary job number. Coordinator must assign these activities to a job number before approving.'
TC-DJ-024 | 44676 | Timesheet Approval - Draft Guard | Verify approval succeeds after the draft job is linked | Confirm the guard clears once the job has an official number | Timesheet previously blocked by a draft job; the coordinator has since linked that draft to a J&E number | 1. As Coordinator, link the draft job to a J&E job number 2. As Approver, re-open the pending timesheet 3. Click Approve | Linked job | No draft warning is shown; the timesheet is approved successfully against the official job number | Functional | High | Pass | After linking DRAFT-10 -> 00194 the TEMP JOB # badge and the warning banner disappeared from timesheet ID#226 and Approve proceeded past the draft guard. |  | Final approval then stopped by an unrelated 'Missing time' validation (employees without clock in/out on this shared dev timesheet).
TC-DJ-025 | 44599 | Jobs Dashboard - Job Cards | Verify updated job card fields on the Open Jobs dashboard | Confirm all card data points render | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open the Open Jobs dashboard 2. Review a job card for a job with full data | Job with tasks, activities, hours and address | Card shows: job number (or temp number), job name (or alias), customer name, job address, job % complete, job total hours, job bid hours, number of tasks, number of activities in progress; styling matches Figma | Functional / UI | High | Pass | Regular cards show all 9 fields (JOB# number, name, customer, address, % progress, job hrs, bid hrs, tasks, activities). Draft cards show temp number, name, address and KPIs; customer blank by design (null customer).
TC-DJ-026 | 44599 | Jobs Dashboard - Job Cards | Verify updated job card fields on the Closed Jobs dashboard | Confirm parity on the closed jobs view | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Open the Closed Jobs dashboard 2. Review a job card | Closed job with data | The same updated card layout and fields are displayed as on the Open Jobs dashboard | Functional / UI | Medium | Pass | Closed jobs dashboard renders the same updated card layout (e.g. JOB# 1021 with all fields and actions).
TC-DJ-027 | 44599 | Jobs Dashboard - Job Cards | Verify temp number displays in the upper-left corner for a draft job card | Confirm draft jobs are identifiable on the dashboard | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the Open Jobs dashboard 2. Locate the draft job's card | Draft job | The temporary job number is displayed in the upper-left corner of the job card (with the TEMP flag styling per Figma) | UI | High | Pass | 'TEMP JOB # DRAFT-xx' badge rendered in the upper-left corner of draft job cards.
TC-DJ-028 | 44599 | Jobs Dashboard - Job Cards | Verify alias displays instead of the formal job number | Confirm alias precedence on the card | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Ensure a job has an alias 2. View that job's card on the dashboard | Job with alias | The alias name is shown on the card in place of the formal job number | Functional | Medium | Pass | Alias displays as card title: job 00136 shows its alias 'Job Draft-06' instead of the formal J&E name (OGLETH TA ST1 INSULATION).
TC-DJ-029 | 44599 | Jobs Dashboard - Job Cards | Verify Details button navigates to Step 1 | Card action navigation - Details | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. On a job card, click the Details button | Any job | User is taken to Job Workbench Step 1 for that job | Functional | High | Pass | Details navigates to the Job Workbench Step 1 for that job (link ?step=1; verified by click).
TC-DJ-030 | 44599 | Jobs Dashboard - Job Cards | Verify Tasks button navigates to Step 3 | Card action navigation - Tasks | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. On a job card, click the Tasks button | Any job | User is taken to Job Workbench Step 3 for that job | Functional | High | Pass | Tasks navigates to Step 3 - Tasks & activities (link ?step=3; step 3 loads for the job).
TC-DJ-031 | 44599 | Jobs Dashboard - Job Cards | Verify Dispatch button navigates to the dispatch screen filtered to the job | Card action navigation - Dispatch (permission-gated) | Coordinator user WITH dispatch permissions is logged in | 1. On a job card, click the Dispatch button 2. Observe the dispatch screen results | User with dispatch permission | User is taken to the dispatch screen and the results are filtered to that job | Functional | High | Pass | As expected
TC-DJ-032 | 44599 | Jobs Dashboard - Job Cards | Verify Timesheets button navigates to pending timesheets filtered to the job | Card action navigation - Timesheets (permission-gated) | Coordinator user WITH approver permissions is logged in | 1. On a job card, click the Timesheets button 2. Observe the pending timesheets list | User with approver permission | User is taken to Pending Timesheets and the results are filtered for that job | Functional | High | Pass | As expected
TC-DJ-033 | 44599 | Jobs Dashboard - Job Cards | Verify job hours display green when bid hours exceed job hours | Threshold coloring - under bid | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Locate a job whose bid hours are greater than its total job hours 2. Observe the job hours value on the card | Job under bid hours | The job hours value is displayed in green per the Figma styling | Functional / UI | Medium | Pass | Job 1006 (21 job hrs < 48 bid hrs): job hrs value rendered green rgb(85,135,23).
TC-DJ-034 | 44599 | Jobs Dashboard - Job Cards | Verify job hours display red when job hours exceed bid hours | Threshold coloring - over bid | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Locate a job whose total job hours exceed its bid hours 2. Observe the job hours value on the card | Job over bid hours | The job hours value is displayed in red per the Figma styling | Functional / UI | Medium | Pass | Jobs 1005 and 1015 (hours over bid): job hrs value rendered red rgb(209,0,0).
TC-DJ-035 | 44599 | Jobs Dashboard - Job Cards | Verify task count on the card matches the job's tasks | Card KPI accuracy - tasks | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Identify a job with a known number of tasks (e.g. 4) 2. Observe the tasks box on its card | Job with 4 tasks | The tasks box shows the exact count (e.g. 4) | Functional | Medium | Pass | Task counts on cards match job data (e.g. 00136 card shows 1 task = its single retained task).
TC-DJ-036 | 44599 | Jobs Dashboard - Job Cards | Verify activities count shows started/total format | Card KPI accuracy - activities in progress | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Identify a job with e.g. 5 labor activities of which 3 are started 2. Observe the activities box on its card | Job with 3 of 5 activities started | The activities count displays as 3/5 | Functional | Medium | Pass | Activities tile displays started/total format (1/1, 3/3, 7/7).
TC-DJ-037 | 44599 | Jobs Dashboard - Job Cards | Verify dashboard loading, empty and error states | Confirm resilient UI states on the job dashboards | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Load the dashboard on first render and observe the loading state 2. Filter so that no jobs are returned 3. Simulate a failed request (e.g. drop network) and observe | No-result filter; network interruption | While loading, a skeleton/spinner is shown; when no data is returned, a clear empty-state message is shown (not a blank grid); on failure a human-readable, non-blocking error is shown (never a raw stack/endpoint), the last good data remains where applicable and the action can be retried | UI / Negative | Medium | Pass | Empty state verified: searching a non-existent job shows 'No results found / Please try again' (not a blank grid). |  | Loading skeleton not observable (data cached client-side); forced network-failure case not executed in the shared dev environment.
TC-DJ-038 | 45855 | Reusable Component - KpiTile | Verify KPI tile renders value with suffix and label | Presentational check via any card using KpiTile | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View a job card KPI tile that has a suffix (e.g. Progress) 2. Observe value and caption | Progress = 40, suffix % | Tile displays '40%' as the primary value with 'Progress' as the caption beneath it | UI | Medium | Pass | Tiles render value with suffix and caption beneath (e.g. '0%' over 'Progress').
TC-DJ-039 | 45855 | Reusable Component - KpiTile | Verify KPI tile without a suffix shows the raw value | Presentational check - no unit appended | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View a KPI tile with a plain numeric value (e.g. task count) 2. Observe the value | Numeric KPI without suffix | The raw value is displayed with no appended unit | UI | Low | Pass | Numeric tiles without suffix show the raw value (e.g. '40' Bid hrs, '1' Tasks).
TC-DJ-040 | 45855 | Reusable Component - KpiTile | Verify KPI tile status colors (neutral / success / warning / error) | Confirm the status-to-color mapping uses the design tokens | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Locate tiles in each state: default (neutral), success, warning and error (e.g. hours under/over bid) 2. Compare colors against the Figma design tokens | Jobs producing each KPI status | Neutral tiles use the light-blue background with brand-primary accent (default); success, warning and error tiles use their corresponding token colors consistently across all cards | UI | Medium | Pass | Neutral tiles use the light-blue background with brand-primary value color; success green, error red and warning-tone TEMP badge all use consistent token colors.
TC-DJ-041 | 45855 | Reusable Component - KpiTile | Verify clickable KPI tile responds to mouse and keyboard | Accessibility and interactivity of actionable tiles | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. Click a KPI tile that has an action 2. Tab to the same tile and activate it with the keyboard (Enter/Space) 3. Attempt to tab to a display-only tile | Card with clickable and display-only tiles | The clickable tile is focusable (button role), triggers its action by click and by keyboard; display-only tiles are not focusable and trigger nothing | Functional / Accessibility | Medium | Pass | Job card KPI tiles are display-only: no role=button, no tabindex, not focusable - correct for tiles without onClick. |  | No clickable KPI tile exists in the current screens, so click/keyboard activation could not be exercised.
TC-DJ-042 | 45856 | Reusable Component - KpiTileRow | Verify tile row renders the configured tiles in order | Row renders N tiles per card persona | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View an approver timesheet card (4 tiles) and a coordinator job card (5 tiles) 2. Count the tiles and check their order | Approver card; coordinator card | Exactly the configured number of tiles render, in the defined order, for each card type | UI | Medium | Pass | Coordinator job cards render 5 tiles; approver timesheet cards render 5 tiles (# employees, # jobs, # tasks, # activities, Total hrs) in the defined order. |  | Approver card is 5 tiles per story 45859 (45856 description's '4 for Approver' is superseded).
TC-DJ-043 | 45856 | Reusable Component - KpiTileRow | Verify tiles distribute evenly and respond to browser width | Responsive layout of the KPI row | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View cards with 4 and 5 tiles 2. Resize the browser window across desktop widths and compare | Various browser widths | Tiles distribute evenly across the available width in both the 4-tile and 5-tile cases with no overlap, truncation or broken layout | UI / Responsive | Medium | Fail | On approver timesheet cards at a standard desktop width the tiles truncate: Total hrs value shows '00:...' and the 'Employees' label is clipped. | BUG-03 | Job-card tile rows distribute correctly; the 5-tile timesheet row does not fit its card width.
TC-DJ-044 | 45857 | KPI Status Thresholds (kpiStatus) | Verify job hours KPI shows error state when job is over bid hours | Threshold resolver - over bid | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View the card/tile for a job whose hours exceed its bid hours 2. Observe the job hours KPI state | Job over bid hours | The job hours KPI renders in the error (red) state | Functional / UI | Medium | Pass | Job over bid hours (1005, 1015): job hrs KPI renders in the error (red) state.
TC-DJ-045 | 45857 | KPI Status Thresholds (kpiStatus) | Verify job hours KPI shows success state when job is under bid hours | Threshold resolver - under bid | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View the card/tile for a job under its bid hours 2. Observe the job hours KPI state | Job under bid hours | The job hours KPI renders in the success (green) state | Functional / UI | Medium | Pass | Job under bid hours with progress (1006): job hrs KPI renders in the success (green) state.
TC-DJ-046 | 45857 | KPI Status Thresholds (kpiStatus) | Verify KPI defaults to neutral when no bid hours / no threshold applies | Threshold resolver - neutral fallback | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View the card/tile for a job with no bid hours or progress 2. Observe the job hours KPI and any KPI without a threshold rule | Job without bid hours | KPIs with no applicable threshold render in the neutral state (default styling) | Functional / UI | Low | Pass | Jobs with no hours/no bid (1156, 89994, 00130 with 0 hrs): KPI renders in the neutral state (brand blue).
TC-DJ-047 | 45858 | Reusable Component - JobCard | Verify card header content and fallbacks for missing fields | Header shows number, title, customer, address with defaults | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View a card for a job with complete data 2. View a card for a job with a missing field (e.g. no address) | Job with full data; job with missing fields | Header shows job number, title, customer name and formatted address; missing fields display the standard fallback value instead of blank/broken layout | UI | Medium | Pass | Headers render number, title, customer and address; draft cards with null customer render cleanly with no broken layout (customer line simply absent).
TC-DJ-048 | 45858 | Reusable Component - JobCard | Verify action buttons render evenly split with dividers; no action row when empty | Card action row layout | User is logged into FieldTrax web as a Coordinator; FieldTrax-ScikIQ test environment is available; at least one service offering is configured | 1. View a card with multiple actions and observe the action row 2. Locate/configure a card with no actions | Cards with and without actions | Actions render as evenly split buttons separated by dividers; when no actions are configured, no action row is displayed | UI | Medium | Pass | Action row renders 4 evenly split buttons (Details/Tasks/Dispatch/Timesheet) with dividers. |  | A card with an empty action list is not producible from the UI, so the 'no action row' half was not exercised.
TC-DJ-049 | 45858 | Reusable Component - JobCard | Verify TEMP flag badge renders next to the job number for draft jobs only | Flag badge behavior | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. View the draft job's card and observe next to the job number 2. View a non-draft job's card | Draft job; regular job | Draft job card shows a 'TEMP' badge next to the job number in the warning tone (shared status tokens); regular job cards show no badge and reserve no space for it | UI | High | Pass | TEMP badge appears next to the temp job number on draft cards in the warning tone; regular job cards show no badge and reserve no space. Badge also disappeared from timesheet ID#226 card after its draft was linked.
TC-DJ-050 | 45859 | Approver - Timesheet Cards | Verify timesheet card header shows ID, employee name and right-aligned date | Timesheet card header content | User is logged into FieldTrax web as an Approver; employee timesheets exist for the period | 1. Open the timesheet review/pending list showing timesheet cards 2. Observe a card's header | Employee timesheet | Header shows the ID# identifier, the employee name as the title, and the timesheet date right-aligned in the format 'Mar 04, 2026' | UI | High | Pass | Timesheet card header shows the ID# chip (e.g. ID# 226), employee name 'Arjun Porwal' as title, and the date 'Aug 26, 2026' right-aligned.
TC-DJ-051 | 45859 | Approver - Timesheet Cards | Verify the five timesheet KPI tiles render in order | Timesheet card KPI content | Approver logged in; timesheet with employees, jobs, tasks, activities and hours | 1. Observe the KPI tiles on a timesheet card | Timesheet with known counts | Five tiles display in order: # of employees, # of jobs, # of tasks, # of activities, Total hours - with values matching the timesheet data | Functional / UI | High | Pass | Five tiles in order: 4 Employees, 2 Jobs, 2 Tasks, 2 Activities, 00:18 Total hrs - matching the timesheet data.
TC-DJ-052 | 45859 | Approver - Timesheet Cards | Verify Total hours tile displays in HH:MM format | Hours formatting | Approver logged in; timesheet with a known total (e.g. 9.5 hours) | 1. Observe the Total hours tile on the timesheet card | 9.5 hours logged | The value displays formatted as HH:MM (e.g. '09:30') | Functional | Medium | Fail | Underlying value is correctly formatted HH:MM (00:18) but the tile renders it truncated as '00:...' at standard desktop width. | BUG-06 | Same defect as TC-043.
TC-DJ-053 | 45859 | Approver - Timesheet Cards | Verify the card shows a single 'Review timesheet' action | Timesheet card action row | Approver logged in | 1. Observe the action row of a timesheet card | N/A | Exactly one action, 'Review timesheet', is displayed on the card | UI | Medium | Pass | Exactly one action - 'Review timesheet' - is displayed on each timesheet card.
TC-DJ-054 | 45859 | Approver - Timesheet Cards | Verify 'Review timesheet' navigates to that employee's timesheet review | Timesheet card navigation | Approver logged in | 1. Click 'Review timesheet' on an employee's card | Employee timesheet | User is navigated to that employee's timesheet review screen | Functional | High | Pass | 'Review timesheet' navigates to that employee's timesheet review (/timesheets/overview/{id}).
TC-DJ-055 | 44020 | End-to-End - Draft Job Lifecycle | E2E - Full draft job lifecycle with data retention | Prove the core feature hypothesis: prep work on a draft survives the link with nothing re-entered | Coordinator and Approver accounts available; J&E job number available for linking | 1. Create a draft job from the Add Job modal (one service offering + 'Assign temporary job number') 2. On the draft: attach documents, set up craft codes, add tasks, dispatch a crew and log time against it 3. Link the draft to the J&E job number via Step 1 (acknowledge + confirm) 4. Re-open the job under the official number and verify every area 5. As Approver, approve the related timesheet | Draft job + documents, craft codes, tasks, dispatch, logged time | All documents, craft mappings, tasks, dispatches and timesheets are retained under the official job number; no second job is created; the timesheet that was blocked while draft can now be approved | End-to-End | High | Pass | Full lifecycle verified: DRAFT-06 (document+task+activity+craft mix) linked to 00136 and DRAFT-10 linked to 00194 with all records retained under the official numbers, same GUID (no duplicate job); previously blocked timesheet passed the draft guard after linking. |  | Timesheet's final approval stopped only by unrelated 'Missing time' data validation.
TC-DJ-056 | 44020 | End-to-End - Draft Job Lifecycle | E2E - Draft jobs are excluded from job search and non-draft job lists | Confirm drafts do not leak into search/pickers for official jobs | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Open the Add Existing Job modal and search the Job Number dropdown for the draft's temp number 2. Use global/job search areas of the web app to search for the draft | Existing draft job | The draft job does not appear in the job search results or in the Add Existing Job job-number dropdown; it is visible only where drafts are expected (e.g. the Open Jobs dashboard with TEMP badge) | Functional / Negative | High | Pass | As expected
TC-DJ-057 | 44020 | End-to-End - Draft Job Lifecycle | E2E - Draft job persists across sessions and displays on the dashboard | Confirm the draft is a durable job row | A draft job exists (created via Add Job modal with 'Assign temporary job number'); user is logged in as Coordinator | 1. Note the draft job's temp number 2. Log out and log back in as the Coordinator 3. Open the Open Jobs dashboard | Existing draft job | The draft job still appears on the Open Jobs dashboard with its temp number and TEMP badge, and can be opened to Step 1 with its data intact | Functional | Medium | Pass

## defects
Defect ID | Severity | Priority | Module / Screen | ADO Story Ref | Failed Test Case(s) | Summary | Steps to Reproduce | Expected Result | Actual Result | Environment | Status | Evidence
BUG-01 | Low | P3 | Add Job Modal | 44664 | TC-DJ-010 | Generic validation message when Add is clicked without a job number | 1. Open Jobs dashboard > Add job 2. Select one service offering and Apply 3. Without selecting a job number (draft checkbox unchecked), click Add | An error telling the coordinator to select a job number (per AC of story 44664). | Generic message 'Missing or invalid information provided.' is shown with the Job number field highlighted red. The message does not tell the user what to fix. | dev | New | #VALUE!
BUG-02 | Medium | P2 | Add Job Modal - job dropdown | 44664 / 44661 | TC-DJ-009, TC-DJ-060 | Job number dropdown ('All' offerings) lists 5 invalid 'null -' entries | 1. Open Jobs dashboard > Add job 2. Select the 'All' service offering option and Apply 3. Open the Job number dropdown and inspect the first entries | Only valid unpublished jobs are listed in 'number - name' format; draft jobs must be excluded from job search. | The first 5 options displayed as 'null -' (rows with a null job number | dev | New | #VALUE!
BUG-03 | Medium | P2 | Approver - timesheet cards (KpiTile/KpiTileRow) | 45859 / 45856 / 45855 | TC-DJ-043, TC-DJ-056 | KPI tiles truncate on timesheet cards - Total hrs shows '00:...' | 1. Log in to web portal of FieldTrax. 2. Open Timesheets > Pending 3. Observe the KPI row on any timesheet card at a standard desktop width | Five tiles distribute evenly with fully visible values and labels; Total hours displays as HH:MM (e.g. 00:18). | The Total hrs value displays truncated as '00:...' and the 'Employees' label is overlapped. The 5-tile row does not fit the card width. | dev | New | #VALUE!